## Sheet1
ID | Test Name | Responsibility | Resources | Deadline | Status | Date completed | Comments
1 | Test Menu | Ivaylo | Manually | 25.10.2021 | completed | 24.10.2021 | Test case run without problems
6 | Test Exit option | Ivaylo | Manually | 25.10.2021 | completed | 25.10.2021 | Works well.
2 | Test Grid sizes | Ivaylo | Manually | 26.10.2021 | completed | 25.10.2021 | No issues while running the code
4 | Test Rules | Ivaylo | Manually | 27.10.2021 | completed | 26.10.2021 | Working properly
5 | Test the previous page button | Ivaylo | Manually | 27.10.2021 | completed | 26.10.2021 | No issues.
3 | Test Player movement | Ivaylo | Manually | 6.11.2021 | completed | 05.11.2021 | Working without a problem
7 | Test the colours in the menu | Ivaylo | Manually