## Sheet1
ID | Test Name | Responsibility | Resources | Deadline | Status | Date completed | Comments
1 | Test menu | Ivaylo Markov | Manually | 25.10.2021 | failed | 24.10.2021 | Issues with colours when you get back from rules to menu
2 | Test exit option | Ivaylo Markov | Manually | 25.10.2021 | completed | 25.10.2021 | Works well
3 | Test grid sizes | Ivaylo Markov | Manually | 26.10.2021 | completed | 25.10.2021 | No issues while running the code
4 | Test rules | Ivaylo Markov | Manually | 27.10.2021 | completed | 26.10.2021 | Working properly
5 | Test the previous page button | Ivaylo Markov | Manually | 27.10.2021 | completed | 26.10.2021 | No issues
6 | Test maze generation algorithm | Ivaylo Markov | Manually | 03.11.2021 | failed | 01.11.2021 | Algorithm generates a straight line shaped maze
7 | Test player movement | Ivaylo Markov | Manually | 06.11.2021 | completed | 06.11.2021 | Working without a problem
8 | Test maze generation algorithm #2 | Ivaylo Markov | Manually | 08.11.2022 | completed | 06.11.2021 | Maze now generates better shapes
9 | Test walls stability | Ivaylo Markov | Manually | 06.11.2021 | completed | 06.11.2021 | Colours look perfect
10 | Test winning message | Ivaylo Markov | Manually | 07.11.2021 | completed | 07.11.2021 | Message works perfect
11 | Test the colours in the menu | Ivaylo Markov | Manually | 08.11.2021 | completed | 08.11.2021 | End works properly
12 | Test maze end | Ivaylo Markov | Manually | 08.11.2021 | completed | 08.11.2021 | Everything passes
13 | Test menu #2 | Ivaylo Markov | Manually | 08.11.2021 | completed | 08.11.2021 | Menu works well
14 | Test choices in play menu | Ivaylo Markov | Manually | 08.11.2021 | completed | 08.11.2021 | Delivers values correctly